## Build later
# | Feature | What it does / why | Needs | Size | Priority | Depends on | Status | Added | Came up from
1 | QuickBooks history import | Owner-pressed one-time import of the last N months of the ledger (default 24, the post-audit reach), one month per Inngest step with throttle backoff and a run row per month so it resumes and re-runs free. Opens cases only inside a dispute cutoff (default 12 months); older short-pays recorded as declines with reason outside_dispute_window so coverage still counts them. Gives 'what you lost over two years, by retailer' on the board — the audit Glimpse sells as its front door. | No ADR, no migration; two settings | 1 day | P1 | QBO connection (built) | Parked | 2026-10-05 | Parth asked how hard 'all historicals' would be
2 | Watched folder sync (Drive / OneDrive / SharePoint / Dropbox) | Connect a cloud folder read-only, scoped to one folder; every new file ingested like an upload. The hands-off way to get PoDs, BoLs and invoices in without forwarding emails. | ADR + migration (new uploads.source); tokens sealed like QuickBooks' | 2 days | P2 | — | Parked | 2026-10-05 | Where do PoDs/BoLs come from
3 | Carrier / 3PL portal read recipes (PoD) | Point the portal-read engine at carrier portals (XPO, Estes, FedEx Freight…) and 3PL portals to pull signed PoDs by PRO/BoL number. | Credentials per carrier; recipe YAML per portal | 1–2 days per carrier | P2 | Portal read engine (built, fixture-only); Frazil's carriers known | Parked | 2026-10-05 | Where do PoDs/BoLs come from
4 | EDI 856 / 214 / 210 / 812 / 820 | Read ASNs, shipment status, freight invoices, deduction (812) and remittance (820) feeds from an EDI mailbox or VAN. Phase 2.5 in the build order. | ADR; new uploads.source edi_812 already reserved | 1–2 weeks | P2 | Frazil's EDI provider | Parked | 2026-10-05 | Where do PoDs/BoLs come from
5 | First live portal read recipe for Frazil's top payer | Read-only Playwright recipe against the payer's real portal (ADR 0057/0062 pattern); captures held by_portal for a person. | Credential sealed in KMS; recipe YAML | 2–3 days | P1 | Oct 14 call: which payers, which portal, read-only user | Waiting on call | 2026-10-04 | Pilot to-do
6 | Filing by recipe on a portal (ADR 0061) | Submit an approved packet on the payer's portal by a deterministic recipe, behind the approval gate. | ADR 0061 accepted; that portal's read first | 3 days | P1 | #5 | Waiting on #5 | 2026-10-04 | Pilot to-do
7 | Seed payer code map from Frazil's own notices | Load payer code → canonical mappings from the customer's notices, confirmed by them (pnpm seed:payer-codes, dry-run first). | Migration 0040 applied; PR #144 merged | 0.5 day | P1 | #144 merged | Waiting on 0040 | 2026-10-04 | Pilot to-do
8 | Dispute deadlines computed from payer rules | Fill the 'no deadline' bucket most ledger and remittance cases sit in, from effective-dated payer windows in the playbook data. | No migration if it lives in playbook YAML → code | 2 days | P1 | Playbook drafts; Frazil's payers | Parked | 2026-10-04 | Pilot to-do
9 | Playbook YAML → code map → evidence checklist per payer | One chain so a new payer is a data file, not code: codes, windows, required documents, channels. | Draft ADR D (playbooks as versioned data) | 3 days | P1 | #7, #8 | Parked | 2026-10-04 | Pilot to-do
10 | Second AccountingSource (NetSuite or Xero) | Only if Frazil is not on QuickBooks Online; otherwise CSV/XLSX export via ADR 0056 covers it. | After QBO, same port | 1 week | Conditional | Oct 14 call: their accounting system | Waiting on call | 2026-10-04 | Pilot to-do
11 | Trial balance / GL snapshots per sync run | Keep a snapshot of the books with each sync for month-end tie-out and post-audit defence (ADR 0066 §4, approved as direction). | Migration (append-only table) | 2 days | P2 | ADR 0066 (accepted) | Parked | 2026-10-04 | Books PR #145
12 | Denial and re-file (second-round dispute) | A lost case is terminal today; allow a re-file with new evidence. | ADR (state machine edge) | 2 days | P2 | — | Parked | 2026-10-04 | Pilot to-do
13 | Daily digest of held documents and approaching deadlines | Email per workspace each morning: what is held, what is due within 14 days. | ADR (new outbound side effect) | 1 day | P2 | Resend already configured | Parked | 2026-10-04 | Pilot to-do
14 | Cash application 'click to match' | Match QuickBooks payments to invoices and deductions in one click; the retention hook Glimpse sells. Our Books reconciliation is the read half. | ADR (writes to QuickBooks) | 1 week | P2 | QBO write-back (built, off) | Parked | 2026-10-04 | Glimpse teardown
15 | Contingency billing from recorded outcomes | Invoice the fee on recovered cash, counting recoveries per surviving duplicate group first (Phase 4). | ADR; fee maths exists | 3 days | P2 | First outcomes (30–90 days into pilot) | Parked | 2026-10-04 | Pilot to-do
16 | Direct-to-storage uploads over 4.5 MB and folder drops | Vercel caps a request at 4.5 MB; big scans and whole folders need direct-to-storage with a scan queue (ADR 0055, proposed). | ADR 0055 accepted; migration | 3 days | P2 | — | Parked | 2026-10-04 | Pilot plan
17 | Phase 2 model decision and calibration | Jev/Claude decision providers in shadow, scored against human decisions; needs ≥30 decisions and ≥50 outcomes from the pilots. | ADRs A–H drafted; Jev access | Weeks | P2 | Pilot data | Parked | 2026-10-04 | Phase 2 plan
18 | c-store / distributor reason codes on the decide form | Slotting, off-invoice/billback, spoils, swell, unsaleables, promo allowance where missing. | ADR if the taxonomy grows | 0.5 day | P0 | — | To do before the call | 2026-10-04 | Pilot to-do
19 | Email-in failure paths (VERIFY-CHECKLIST §5.6–5.8) | Forged headers, unaligned sender, oversize mail, wrong secret — exercised before Frazil gets an address. | Production run | 0.5 day | P0 | — | To do before the call | 2026-10-04 | Pilot to-do
20 | Dense remittance: step per part (ADR 0053 §6) | A 190-row distributor remittance reads in 344 s, past the 300 s job limit; run each two-page part as its own step. | Founder's pick of the three options | 1 day | P0 | — | To do before the call | 2026-10-04 | Pilot to-do
21 | Link an unmatched retailer name from the app | Today it is pnpm link:retailer on the command line; a Settings → Retailers page to add a debtor alias and re-home the open cases. | No migration (same write path) | 1 day | P1 | — | Parked | 2026-10-04 | Board PR #142
22 | Say on the page when suggestions were withheld | After PR #148 a document whose candidate read hit the cap gets no suggestion silently; the list should say so. | No migration | 0.5 day | P2 | — | Parked | 2026-10-04 | Audit PR #148
23 | Delegated read-only portal user as the default credential model | Ask every payer for a read-only supplier login rather than the customer's password; password hand-off only when nothing else exists. | Onboarding doc + recipe field | 0.5 day | P2 | — | Parked | 2026-10-04 | Glimpse teardown

## Summary
Build-later backlog — summary
Priority | Items | Not yet built
P0 | 3 | 3
P1 | 7 | 7
P2 | 12 | 12
Conditional | 1 | 1
Total | 23 | 23
Legend: P0 = before the Oct 14 Frazil call · P1 = first two weeks of the pilot · P2 = after · Conditional = only if the call says so. Sizes are rough agent-days. 'Needs' says whether an ADR or a migration (founder applies by hand) is required.